## Sheet1
Time in hours | Time in Hours |  | Name | In Progress | Name | Complete
1 |  | Read only bug |  |  | Chris | main.cc implementation
| 1 | bug fix |  |  | Chris | CPL implementation
2 |  | CPL Multiple Files |  |  | Chris | OPL implementation
| 0.5 | main.cc implementation
| 0.5 | CPL implementation |  |  | Zach | Read only Bug
| 0.5 | Writing tests |  |  | Zach | Tested read only bug
| 0.25 | Running Tests
| 0.25 | Test Logging
1.5 |  | OPL multiple Files
| 0.5 | OPL implementation
| 0.5 | Writing tests
| 0.25 | Running Tests
| 0.25 | Test Logging
4.25 |  | MPO Files
| 0.25 | MPO.h
| 0.25 | MPO.cc
| 1 | read header
| 1 | read ballot
| 1 | Writing tests
| 0.5 | Running Tests
| 0.25 | Test Logging
1 |  | MPO Multiple Files
| 0.5 | Writing tests
| 0.25 | Running Tests
| 0.25 | Test Logging
3.25 |  | MPO Election
| 1 | Extract Popular Candidate
| 0.5 | Calculate Winners
| 1 | Writing tests
| 0.5 | Running Tests
| 0.25 | Test Logging
3.25 |  | MV Files
| 0.25 | MV.h
| 0.25 | MV.cc
| 1 | read ballots
| 1 | Writing tests
| 0.5 | Running Tests
| 0.25 | Test Logging
1 |  | MV Multiple Files
| 0.5 | Writing tests
| 0.25 | Running Tests
| 0.25 | Test Logging
2 |  | MV Election
| 0.25 | Calculate Winners
| 1 | Writing tests
| 0.5 | Running Tests
| 0.25 | Test Logging
1.75 |  | MPO Stats to Screen
| 0.5 | output file
| 0.25 | output screen
| 0.5 | Writing tests
| 0.25 | Running Tests
| 0.25 | Test Logging
1.5 |  | MV Stats to Screen
| 0.25 | output file
| 0.25 | output screen
| 0.5 | Writing tests
| 0.25 | Running Tests
| 0.25 | Test Logging
2.5 |  | Documentation
10 |  | System Testing
| 6 | Writing tests
| 3 | Running Tests
| 1 | Test Logging