## Sheet1
Time in hours | Time in Hours |  | Name | In Progress | Name | Complete
1 |  | Read only bug |  |  | Chris | main.cc implementation
| 1 | bug fix |  |  | Chris | CPL implementation
2 |  | CPL Multiple Files |  |  | Chris | OPL implementation
| 0.5 | main.cc implementation
| 0.5 | CPL implementation |  |  | Zach | Read only Bug
| 0.5 | Writing tests |  |  | Zach | Tested read only bug
| 0.25 | Running Tests |  |  | Zach | Writing tests CPL files
| 0.25 | Test Logging |  |  | Zach | Writing tests OPL files
1.5 |  | OPL multiple Files |  |  | Zach | Test log CPL files
| 0.5 | OPL implementation |  |  | Zach | Test log OPL files
| 0.5 | Writing tests |  |  | Zach | Running test CPL files
| 0.25 | Running Tests |  |  | Zach | Running test OPL files
| 0.25 | Test Logging |  |  | Zaid | main.cc implementation
1 |  | Create MPO Ballot Maker |  |  | Zaid | Running test CPL files
4.25 | 0.25 | MPO Files
| 0.25 | MPO.h |  |  | Chris | MPO.h
| 1 | MPO.cc |  |  | Chris | MPO.cc
| 1 | read header |  |  | Chris | MPO read header
| 1 | read ballot | Zaid | Doxy comments for MPO header | Chris | MPO read ballot
| 0.5 | Writing tests |  |  | Chris | Extract Popular Candidate
| 0.25 | Running Tests |  |  | Chris | MPO Calculate Winners
1 |  | Test Logging | Zaid | gtest CPL unit tests | Chris | MPO output screen
| 0.5 | MPO Multiple Files | Zaid | gtest MPO unit tests
| 0.25 | Writing tests |  |  | Zach | Test log MPO files
| 0.25 | Running Tests | Zaid | add more gtest OPL unit tests | Zach | Test log MPO multi files
3.25 |  | Test Logging | Zaid | Check program for memory leaks | Zach | Create MPO ballot maker
| 1 | MPO Election | Zaid | Party Map tests | Zach | Writing tests MPO files
| 0.5 | Extract Popular Candidate | Zaid | Log test results for google tests | Zach | Writing tests MPO multi files
| 1 | Calculate Winners | Zaid | update Readme | Zach | Running test MPO files
| 0.5 | Writing tests |  |  | Zach | Running test MPO multi files
| 0.25 | Running Tests | Zaid | MV writing tests | Zach | MV.h
3.25 |  | Test Logging | Zaid | MV Running Tests | Zach | MV.cc
| 0.25 | MV Files | Zaid | MV Test Logging | Zach | MV read ballot
| 0.25 | MV.h | Zaid | MV Stats to screen | Zach | MV Calculate Winners
| 1 | MV.cc |  |  | Zach | MV Stats to Screen
| 1 | read ballots |  |  | Zach | MV Ballot creator
| 0.5 | Writing tests |  |  | Zach | MPO output File
| 0.25 | Running Tests |  |  | Zach | MV output File
1 |  | Test Logging | Zaid | MPO Files Writing tests | Zach | MV multi files
| 0.5 | MV Multiple Files | Zaid | MPO Files Running Tests | Zach | MV Multi test writing
| 0.25 | Writing tests | Zaid | MPO Files Test Logging | Zach | MV Multi test logging
| 0.25 | Running Tests | Zaid | MV Files Writing tests | Zach | MV Multi test running
2 |  | Test Logging | Zaid | MV Files Running Tests | Zaid | Created new Makefile to be able to run tests
| 0.25 | MV Election | Zaid | MV Files Test Logging | Zaid | google style OPL unit tests
| 1 | Calculate Winners |  |  | Zaid | fixed segfault error
| 0.5 | Writing tests
| 0.25 | Running Tests
1.75 |  | Test Logging
| 0.5 | MPO Stats to Screen
| 0.25 | output file
| 0.5 | output screen
| 0.25 | Writing tests
| 0.25 | Running Tests
1.5 |  | Test Logging
| 0.25 | MV Stats to Screen
| 0.25 | output file
| 0.5 | output screen
| 0.25 | Writing tests
| 0.25 | Running Tests
2.5 |  | Test Logging
10 |  | Documentation
| 0.25 | Run Doxygen