## Sheet1
Time in hours | Time in Hours |  | Name | In Progress | Name | Complete
1 |  | Read only bug | Zaid | Party Map tests | Chris | main.cc implementation
| 1 | bug fix | Zaid | Miscalculation Bug | Chris | CPL implementation
2 |  | CPL Multiple Files |  |  | Chris | OPL implementation
| 0.5 | main.cc implementation
| 0.5 | CPL implementation |  |  | Zach | Read only Bug
| 0.5 | Writing tests |  |  | Zach | Tested read only bug
| 0.25 | Running Tests |  |  | Zach | Writing tests CPL files
| 0.25 | Test Logging |  |  | Zach | Writing tests OPL files
1.5 |  | OPL multiple Files |  |  | Zach | Test log CPL files
| 0.5 | OPL implementation |  |  | Zach | Test log OPL files
| 0.5 | Writing tests |  |  | Zach | Running test CPL files
| 0.25 | Running Tests |  |  | Zach | Running test OPL files
| 0.25 | Test Logging |  |  | Zaid | main.cc implementation
1 |  | Create MPO Ballot Maker |  |  | Zaid | Running test CPL files
4.25 | 0.25 | MPO Files
| 0.25 | MPO.h |  |  | Chris | MPO.h
| 1 | MPO.cc |  |  | Chris | MPO.cc
| 1 | read header |  |  | Chris | MPO read header
| 1 | read ballot |  |  | Chris | MPO read ballot
| 0.5 | Writing tests |  |  | Chris | Extract Popular Candidate
| 0.25 | Running Tests |  |  | Chris | MPO Calculate Winners
1 |  | Test Logging |  |  | Chris | MPO output screen
| 0.5 | MPO Multiple Files
| 0.25 | Writing tests |  |  | Zach | Test log MPO files
| 0.25 | Running Tests |  |  | Zach | Test log MPO multi files
3.25 |  | Test Logging |  |  | Zach | Create MPO ballot maker
| 1 | MPO Election |  |  | Zach | Writing tests MPO files
| 0.5 | Extract Popular Candidate |  |  | Zach | Writing tests MPO multi files
| 1 | Calculate Winners |  |  | Zach | Running test MPO files
| 0.5 | Writing tests |  |  | Zach | Running test MPO multi files
| 0.25 | Running Tests |  |  | Zach | MV.h
3.25 |  | Test Logging |  |  | Zach | MV.cc
| 0.25 | MV Files |  |  | Zach | MV read ballot
| 0.25 | MV.h |  |  | Zach | MV Calculate Winners
| 1 | MV.cc |  |  | Zach | MV Stats to Screen
| 1 | read ballots |  |  | Zach | MV Ballot creator
| 0.5 | Writing tests |  |  | Zach | MPO output File
| 0.25 | Running Tests |  |  | Zach | MV output File
1 |  | Test Logging |  |  | Zach | MV multi files
| 0.5 | MV Multiple Files |  |  | Zach | MV Multi test writing
| 0.25 | Writing tests |  |  | Zach | MV Multi test logging
| 0.25 | Running Tests |  |  | Zach | MV Multi test running
2 |  | Test Logging |  |  | Zaid | Created new Makefile to be able to run tests
| 0.25 | MV Election |  |  | Zaid | gtest OPL multiple file unit tests written
| 1 | Calculate Winners |  |  | Zaid | gtest CPL multiple file unit tests written
| 0.5 | Writing tests |  |  | Zaid | gtest OPL multiple file unit tests ran
| 0.25 | Running Tests |  |  | Zaid | gtest CPL multiple file unit tests ran
1.75 |  | Test Logging |  |  | Zaid | fixed segfault error
| 0.5 | MPO Stats to Screen |  |  | Zaid | Doxy comments edited for MV header
| 0.25 | output file |  |  | Zaid | Doxy comments edited for MPO header
| 0.5 | output screen |  |  | Zaid | Check program for memory leaks
| 0.25 | Writing tests |  |  | Zaid | OPL multiple file tests logged
| 0.25 | Running Tests |  |  | Zaid | CPL multiple file tests logged
1.5 |  | Test Logging |  |  | Zaid | MV Files Writing tests
| 0.25 | MV Stats to Screen |  |  | Zaid | MPO Files Writing tests
| 0.25 | output file |  |  | Zaid | update Readme
| 0.5 | output screen |  |  | Zaid | MV Stats to screen
| 0.25 | Writing tests |  |  | Zaid | MPO Files Running Tests
| 0.25 | Running Tests |  |  | Zaid | MV Files Running Tests
2.5 |  | Test Logging |  |  | Zaid | MPO Files Test Logging
10 |  | Documentation |  |  | Zaid | MV Files Test Logging
| 0.25 | Run Doxygen